## Sheet1
Project Plan - EDCI 337 - Assignment 4
Use this form to plan your tasks and assign responsibility to one or more group members |  |  |  |  | Group K : Stella Yan / Cyan Liu / Junze Bian / Jacky Li |  |  | / Guanhua Wang
Tasks | Timeline |  |  |  |  | Responsible
| Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Proposal | x |  |  |  |  | All members | Stella Yan : Read/Whatch 、To do this week Cyan Liu：Lesson Objectives, application, reference collation Junze Bian: Content Jacky Li: Reflection Guanhua Wang：Complement and improve information
Draft Lesson Plan | x |  |  |  |  | All members | Stella Yan : Big Idea Cyan Liu : Learning Outcome(s) Junze Bian: Evidence of Learning, Assessments Jacky Li: Learning Activities Guanhua Wang:Improve the content
Draft Project Plan | x |  |  |  |  | All members | Stella Yan : Responsible Schedule Cyan Liu: Filling detail Junze Bian: Filling detail Jacky Li: Filling detail Guanhua Wang:Filling detail
Final Proposal |  | x | x |  |  | Stella Yan/Cyan Liu/Jacky Li | Stella Yan: To to week/ Read watch / References Cyan Liu: Overview/ Lesson objectives Jacky Li: Reflection/ Content(PowerPoint)
Final Lesson Plan |  | x | x |  |  | Cyan Liu | All (Big idea,Learning outcome,Evidence of Learning,Assessment,Activites)
Final Project Plan |  | x | x |  |  | Stella Yan/Cyan Liu | Filling detail
H5P (Pop Quiz) |  |  | x | x | x | Stella Yan | Stella Yan : H5p Insert
H5P (Warm up Quiz) |  |  | x | x | x | Stella Yan/Cyan Liu | Stella Yan : H5p Insert Cyan Liu:Text
H5P (Card) |  |  | x | x | x | Stella Yan | Stella yan :H5p Insert
Video |  |  |  | x | x | Cyan Liu/Junze Bian/ Guanhua Wang | Cyan Liu : Video Editing,Video Background Audio， Video Caption， Guanhua Wang：Voice-over and Video， Junze Bian：Play Tai Chi
Blog Posted |  |  |  | x | x | Stella Yan | All the Post,design,Typesetting
Mayers |  |  |  | x | x | Cyan Liu | All
Instructional Design Model |  |  |  | x | x | Cyan Liu | All